## Sheet1
Requirement ID | Description of Requirement | Story Points | Priority | Sprint No.
1 | Get the robot to pick up a game piece | 5 | 2 | 2
2 | Get the robot to scan a game piece | 5 | 2 | 2
3 | Move robot arm from our code | 5 | 2 | 1
4 | Move robot fingers from our code | 5 | 2 | 2
5 | Have the robot analyze the current game state | 8 | 3 | 3
6 | Robot interacting with player during gametime | 8 | 6 | 6
7 | Get the robot to move according to how we want: Moving from just controlling it to making it act with intent. | 8 | 2 | 2
8 | Research how these robots are used: what kind of runtime we expect, internal logic processing, and what interactions are possible | 3 | 1 | 1
9 | Decide what game we want the robot to play | 1 | 1 | 1
10 | Define the game rules | 3 | 3 | 3
11 | Define the game environment (board, cards, pieces, etc.) | 2 | 3 | 3
12 | Define strategy for the game | 5 | 3 | 3
13 | Translate strategy into requirements for the robot | 5 | 4 | 4
14 | Implement strategy into robot's actions | 3 | 4 | 4
15 | Design state machine for robot's actions | 5 | 4 | 4
16 | Implement state machine in robot. | 8 | 4 | 4
17 | Make robot say things during certain decisions | 3 | 6 | 6
18 | Research designs for things like piece holders to make picking things up easier for robot | 2 | 2 | 2
19 | Research additional needed software for the robot | 2 | 2 | 1
20 | Design multiple difficulty levels for the robot | 8 | 5 | 5
21 | Learn how to program the robot and make it execute simple instructions | 13 | 1 | 1
22 | Implement robot gestures | 3 | 6 | 6
23 | Implement the robot's rules tutorial | 5 | 5 | 5
24 | Implement the robot's objective tutorial | 3 | 5 | 5
25 | Implement the robot's strategy tutorial | 8 | 5 | 5